## Sheet1
Defect Log
Count | 1
Total Open | 1
QA Tester | Arikpo Ebri
Project Title: | Swipe Web Application | [12 empty] | Issue Log
Issue # | Issue Description (Steps) | Actual Behaviour | Date Opened | Criticality | Issue Type | Expected Behaviour | Evidence (Screenshot) | Owner | Status | Dev Comment | Dev Status | Plannned Close Date | Actual Date Closed | No of Days Open
SA_001 | Test Case: Ensure a user can add a song to his/her playlist | System displayed an error: "Unable to add song to playlist. Please try again later" | 27th April '23 | High | Defect | Expected Result: User should be able to add a song to their playlist successfully. |  | SwipeTech-Limited | Open
SA_003 | Test Case: Ensure customer can view and input delivery location | Customer is unable to view and input delivery location | 1st Sptember '22 | High | Defect | Expected Result: The system should contain delievery location so as to enable customer view and input desired delivery location. |  | SwipeTech-Limited | Fail
SA_004 | Test Case: Ensure customer can select and view images contained in "Fashion" menu | Upon selecting "Fashion" from the list of avaliable category, system displayed "Chocolate Chips" image | 1st Sptember '22 | High | Defect | The Expected result: System should display corresponding Fashion images only to avoid misinformation |  | SwipeTech-Limited | Fail
SA_005 | Test Case: Ensure customer can select and view images contained in "Beauty" menu | Upon selecting "Beauty" from the list of avaliable category, system displayed "Chocolate Chips" image | 1st Sptember '22 | High | Defect | The Expected result: System should display corresponding Beauty images only to avoid misinformation |  | SwipeTech-Limited | Fail
SA_006 | Test Case: Ensure customer can select and view images contained in "Grunrge" menu | Upon selecting "Grunrge" from the list of avaliable category, system displayed "Chocolate Chips" image | 1st Sptember '22 | High | Defect | The Expected result: System should display corresponding grunrge images only to avoid misinformation |  | SwipeTech-Limited | Fail
SA_007 | Test Cases: Ensure customer can select and view images contained in "Cuoture" menu | Upon selecting "Cuoture" from the list of avaliable category, system displayed "Chocolate Chips" image | 1st Sptember '22 | High | Defect | The Expected result: System should display corresponding Cuoture images only to avoid misinformation |  | SwipeTech-Limited | Fail
SA_008 | Test Cases: Ensure customer can select and view images contained in "Artsy" menu | Upon selecting "Artsy" from the list of avaliable category, system displayed "Chocolate Chips" image | 2nd Sptember '22 | High | Defect | The Expected result: System should display corresponding Artsy images only to avoid misinformation |  | SwipeTech-Limited | Fail
SA_010